## Execution Results
PrestaShop Demo — Test Execution Results
Phase 2: Test Execution ¦ Tester: QA Engineer ¦ Date: 2026-03-14 ¦ Browser: Chrome (latest) ¦ Standard: ISTQB CTFL
✅ PASS: 19 ¦ ❌ FAIL: 4 ¦ ⚠️ BLOCKED: 1 ¦ ⬜ NOT EXECUTED: 1 ¦ Total: 25 ¦ Bugs Found: 4
TC ID | Test Name | Req. ID | Execution Date | Tester | Status | Notes
TC-001 | Successful User Registration with Valid Data | REQ-01 | 2026-03-14 | QA Engineer | ✅ PASS | Account creation flow works correctly. User redirected to account dashboard after registration.
TC-002 | User Registration with Already Registered Email | REQ-01 | 2026-03-14 | QA Engineer | ✅ PASS | System correctly rejects duplicate email: 'An account using this email address has already been registered.'
TC-003 | User Registration with Missing Required Fields | REQ-01 | 2026-03-14 | QA Engineer | ✅ PASS | HTML5 browser-native validation triggers on First Name field first. Subsequent fields validated sequentially on resubmission.
TC-004 | Successful User Login with Valid Credentials | REQ-02 | 2026-03-14 | QA Engineer | ✅ PASS | Login with pub@prestashop.com succeeds. User name displayed in top navigation bar.
TC-005 | User Login with Invalid Credentials | REQ-02 | 2026-03-14 | QA Engineer | ✅ PASS | System returns 'Authentication failed.' in red alert. No account existence info disclosed.
TC-006 | User Login with Empty Fields | REQ-02 | 2026-03-14 | QA Engineer | ✅ PASS | HTML5 required-field validation prevents submission. 'Please fill out this field.' shown on email input.
TC-007 | Successful User Logout | REQ-03 | 2026-03-14 | QA Engineer | ✅ PASS | Session terminated correctly. Sign in link restored. Back navigation does not re-authenticate.
TC-008 | Browse Products by Category | REQ-04 | 2026-03-14 | QA Engineer | ✅ PASS | Category pages load with product grid, breadcrumb, and category title.
TC-009 | Browse Products Using Homepage Featured Section | REQ-04 | 2026-03-14 | QA Engineer | ✅ PASS | Featured product cards on homepage navigate to correct product detail pages.
TC-010 | Search Products with a Valid Keyword | REQ-05 | 2026-03-14 | QA Engineer | ✅ PASS | Searching 'shirt' returns relevant results. Product count shown on SEARCH RESULTS page.
TC-011 | Search Products with an Invalid Keyword | REQ-05 | 2026-03-14 | QA Engineer | ✅ PASS | Searching non-existent keyword returns: 'No results were found for your search.' No error.
TC-012 | Search Autocomplete Suggestions on Keyword Input | REQ-05 | 2026-03-14 | QA Engineer | ❌ FAIL | Empty search bypasses client-side validation and redirects to results page instead of blocking. → BUG-001
TC-013 | View Complete Product Details Page | REQ-06 | 2026-03-14 | QA Engineer | ✅ PASS | All required elements present: name, price, images, size dropdown, color swatches, quantity input, ADD TO CART.
TC-014 | View and Navigate Product Image Gallery | REQ-06 | 2026-03-14 | QA Engineer | ✅ PASS | Thumbnail clicks change main image without page reload. Gallery images load fully.
TC-015 | Filter Products by Size Attribute on Category Page | REQ-07 | 2026-03-14 | QA Engineer | ✅ PASS | Size filter successfully narrows listing. Active filter indicator displayed.
TC-016 | Filter Products by Color Attribute on Category Page | REQ-07 | 2026-03-14 | QA Engineer | ✅ PASS | Color filter works correctly. Removing filter restores full listing.
TC-017 | Sort Product Listing by Price Low to High | REQ-07 | 2026-03-14 | QA Engineer | ✅ PASS | Products reordered ascending by price. Sort dropdown label updated.
TC-018 | Add a Single Product to Shopping Cart | REQ-08 | 2026-03-14 | QA Engineer | ❌ FAIL | System silently adds product with default attributes (Size: S, Color: White) without prompting user to confirm. → BUG-002
TC-019 | Add Multiple Quantities of a Product to Cart | REQ-08 | 2026-03-14 | QA Engineer | ✅ PASS | Qty 3 reflected correctly in cart modal. Total = unit price × 3.
TC-020 | Update Product Quantity in Shopping Cart | REQ-09 | 2026-03-14 | QA Engineer | ❌ FAIL | Setting quantity to 0 immediately removes item without confirmation dialog. → BUG-003
TC-021 | Remove a Product from Shopping Cart | REQ-10 | 2026-03-14 | QA Engineer | ✅ PASS | Trash icon removes item. Cart counter decrements. Empty cart state shown when last item removed.
TC-022 | Remove All Items — Verify Empty Cart State | REQ-10 | 2026-03-14 | QA Engineer | ✅ PASS | 'There are no more items in your cart.' displayed correctly after last item removal.
TC-023 | Full Guest Checkout Process — End-to-End | REQ-11 | 2026-03-14 | QA Engineer | ⚠️ BLOCKED | T&C link in checkout returns 404 in demo environment. Cannot verify guest checkout completion. → BUG-004
TC-024 | Checkout — Address Step Validation with Missing Fields | REQ-11 | 2026-03-14 | QA Engineer | ✅ PASS | Validation messages shown: 'Address is required', 'City is required', 'Zip/Postal Code is required.'
TC-025 | Checkout — Payment Method Selection and Order Submit | REQ-11 | 2026-03-14 | QA Engineer | ⬜ NOT EXECUTED | Dependent on TC-023 which was BLOCKED. Cannot execute payment step without completing prior checkout steps.

## Bug Reports
Bug Reports Summary — PrestaShop Demo
Phase 2: Test Execution ¦ Date: 2026-03-14 ¦ Tester: QA Engineer ¦ Total Bugs: 4
Bug ID | Related TC | Title | Severity | Priority | Status
BUG-001 | TC-012 | Empty search query bypasses client-side validation | Minor | Low | Open
BUG-002 | TC-018 | Add to Cart silently applies default attributes without prompting user | Major | High | Open
BUG-003 | TC-020 | Cart quantity set to 0 removes item instantly without confirmation dialog | Major | High | Open
BUG-004 | TC-023 | Terms & Conditions link returns 404, blocking guest checkout completion | Critical | High | Open

## Summary Dashboard
Test Execution Summary Dashboard
PrestaShop Functional Testing · Phase 2 · 2026-03-14
Status | Count | % of Total
✅ PASS | 19 | 76%
❌ FAIL | 4 | 16%
⚠️ BLOCKED | 1 | 4%
⬜ NOT EXECUTED | 1 | 4%
TOTAL | 25 | 100%
Coverage by Feature Area
Feature Area | Req. IDs | # TCs | FAIL / BLOCKED
Account Features | REQ-01, REQ-02, REQ-03 | 7 | 0 FAIL
Product Features | REQ-04, REQ-05, REQ-06, REQ-07 | 10 | 1 FAIL (TC-012)
Shopping Features | REQ-08, REQ-09, REQ-10, REQ-11 | 8 | 2 FAIL + 1 BLOCKED (TC-018, TC-020, TC-023)